## Dashboard
MikeYe.com M&A Deal Workflow Checklist
Version 1.1 · November 2026 · 156 buyer-side actions, 13 decision gates, deal-team roles and a decision log, from mandate to post-close review.
How to use | Start at the phase you are in. Put a name and a date on each action, filter by phase or gate, and don't clear a gate until its evidence is in. Use Scope decision to drop actions that don't apply. Removed actions drop out of every count below.
Priority | Critical means the action can stop or reprice the deal if it goes wrong. High means it matters but can usually be handled in the contract or the plan.
Where the deal stands | Now | What it tells you
Actions in scope | 156 | Rows still in play after Remove and N/A.
Complete | 0 | Finished, with the evidence in the Ready column.
% complete | 0% | Share of in-scope actions finished.
In progress | 0 | Work under way.
Blocked | 0 | Stuck. Each one needs a named fix or an escalation.
Overdue | 0 | Past the target date and not done.
Open Critical actions with no owner | 43 | Assign these first. Nobody owns work that can stop the deal.
Next gate to clear | Gate 0 | First gate not yet approved on the Stage Gates tab.
Open decisions | 0 | Logged decisions still waiting on an answer.
If unresolved | Open | What it means
Investigate | 24 | Evidence is missing, contradictory or not yet tested. Name what is missing and who is getting it.
Price | 27 | The issue changes standalone value, required investment, financing or returns.
Protect | 81 | Handle it through structure, contract, consent, retention, control or the integration plan.
Walk | 24 | The downside, a transfer failure, a ceiling breach or an integrity issue breaks the thesis.
Progress by phase | Actions | Complete | Blocked | % complete
M&A Mandate | 8 | 0 | 0 | 0%
Thesis & Guardrails | 10 | 0 | 0 | 0%
Target Universe | 10 | 0 | 0 | 0%
First Look & Access | 10 | 0 | 0 | 0%
Initial Underwriting | 12 | 0 | 0 | 0%
IOI / LOI | 12 | 0 | 0 | 0%
Diligence Mobilization | 10 | 0 | 0 | 0%
Confirmatory Diligence | 15 | 0 | 0 | 0%
Structure & Negotiation | 13 | 0 | 0 | 0%
Approval & Signing | 12 | 0 | 0 | 0%
Sign-to-Close | 12 | 0 | 0 | 0%
Closing & Day 1 | 12 | 0 | 0 | 0%
First 100 Days | 12 | 0 | 0 | 0%
Post-Close Review | 8 | 0 | 0 | 0%
Formulas:
Now = COUNTIFS(DealWorkflowTable[Target date],"<"&TODAY(),DealWorkflowTable[Status],"<>Complete",DealWorkflowTable[Status],"<>N/A",DealWorkflowTable[Scope decision],"<>Remove")

## Deal Workflow
Comprehensive M&A Deal Workflow Checklist
Start at the phase you are in. Each row is one action: give it an owner and a date, update Status as the work moves, and use Scope decision to drop rows that do not apply. Yellow columns are yours to fill in.
ID | Phase | Decision gate | Workstream | Action | Ready evidence / output | Why it matters | If unresolved | Priority | Accountable owner | Target date | Status | Dependency / handoff | Related MikeYe.com tool | Scope decision | Reviewer notes
DW-001 | M&A Mandate | Gate 0 — Mandate | Strategy & Thesis | State why acquisition is a better path than building, partnering or doing nothing. | Written make-buy-partner comparison | Prevents M&A from becoming the default answer to a strategy question. | Walk | Critical |  |  | Not Started | Corporate strategy |  | Keep
DW-002 | M&A Mandate | Gate 0 — Mandate | Strategy & Thesis | Define the business problem or opportunity the acquisition must solve. | One-sentence mandate | A clear mandate makes target selection and later diligence testable. | Investigate | High |  |  | Not Started | Corporate strategy |  | Keep
DW-003 | M&A Mandate | Gate 0 — Mandate | Strategy & Thesis | Identify capabilities, markets, customers or economics the buyer needs. | Capability and market gap list | The target should fill a specific gap, not simply look attractive. | Investigate | High |  |  | Not Started | Mandate |  | Keep
DW-004 | M&A Mandate | Gate 0 — Mandate | Governance & Decisions | Name the executive sponsor, deal lead and decision authority. | Approved governance map | Unclear authority slows the process and lets sponsorship substitute for evidence. | Protect | High |  |  | Not Started | Mandate |  | Keep
DW-005 | M&A Mandate | Gate 0 — Mandate | Financing & Cash | Set the available capital, financing constraints and required return approach. | Capital envelope and return criteria | Bankability and buyer type shape what can be paid and how returns should be judged. | Price | Critical |  |  | Not Started | Treasury and finance input | Company valuation models | Keep
DW-006 | M&A Mandate | Gate 0 — Mandate | Governance & Decisions | Set prohibited exposures and non-negotiable compliance requirements. | Risk guardrails | A fatal condition should not be offset by attractive features elsewhere. | Walk | Critical |  |  | Not Started | Legal and compliance input |  | Keep
DW-007 | M&A Mandate | Gate 0 — Mandate | People & Knowledge | Confirm internal capacity and the outside advisors likely to be needed. | Team capacity and advisor plan | A deal process competes with operating work and requires credible owners. | Protect | High |  |  | Not Started | Governance map |  | Keep
DW-008 | M&A Mandate | Gate 0 — Mandate | Governance & Decisions | Approve the mandate before target work begins. | Gate 0 approval record | This is the first irreversible allocation of time, access and reputation. | Walk | Critical |  |  | Not Started | All mandate actions | Decision Log tab | Keep
DW-009 | Thesis & Guardrails | Gate 1 — Thesis | Strategy & Thesis | Describe the opportunity as an experienced buyer would describe it internally. | One-sentence acquisition thesis | Frame before detail. Do not inherit the seller's story. | Investigate | High |  |  | Not Started | Approved mandate |  | Keep
DW-010 | Thesis & Guardrails | Gate 1 — Thesis | Strategy & Thesis | List what must be true for the thesis to work. | Testable thesis conditions | Diligence should test the investment case, not collect documents without direction. | Investigate | High |  |  | Not Started | Acquisition thesis | Due Diligence Checklist | Keep
DW-011 | Thesis & Guardrails | Gate 1 — Thesis | Valuation & Returns | Separate standalone value, seller-created improvements and buyer-created synergies. | Value bridge definitions | Buyer-created synergy belongs to the buyer and does not increase standalone value. | Price | Critical |  |  | Not Started | Acquisition thesis | Company valuation models | Keep
DW-012 | Thesis & Guardrails | Gate 1 — Thesis | Valuation & Returns | Set an initial valuation method and a private hard ceiling framework. | Valuation approach and ceiling method | Scarcity can justify continued access, but it does not override the ceiling. | Price | Critical |  |  | Not Started | Capital envelope | Company valuation models | Keep
DW-013 | Thesis & Guardrails | Gate 1 — Thesis | Strategy & Thesis | Define the combined revenue and margin downside the deal must survive. | Downside case requirements | The downside must remain financeable and survivable before the buyer advances. | Walk | Critical |  |  | Not Started | Return criteria | Company valuation models | Keep
DW-014 | Thesis & Guardrails | Gate 1 — Thesis | Strategy & Thesis | Define acceptable category position, market growth and evidence for scarcity. | Market screen criteria | Claimed defensibility receives no credit until evidence supports it. | Investigate | High |  |  | Not Started | Acquisition thesis | Public Company Comps Workbench | Keep
DW-015 | Thesis & Guardrails | Gate 1 — Thesis | Targeting & Outreach | Set minimum ownership, control and consent requirements. | Control criteria | A seller who cannot deliver control is usually an early stop. | Walk | Critical |  |  | Not Started | Risk guardrails |  | Keep
DW-016 | Thesis & Guardrails | Gate 1 — Thesis | Operations & Workflows | Define which people, contracts, licenses, data, systems and workflows must transfer. | Transferability conditions | Reported performance has little acquisition value if its causes do not survive ownership change. | Protect | High |  |  | Not Started | Acquisition thesis | Due Diligence Checklist | Keep
DW-017 | Thesis & Guardrails | Gate 1 — Thesis | Integration & Synergies | State what must be protected, what could be integrated early and what may stay separate. | Initial integration principles | Protect revenue while integrating cost. Sequence change from the thesis. | Protect | High |  |  | Not Started | Transferability conditions | Integration Checklist | Keep
DW-018 | Thesis & Guardrails | Gate 1 — Thesis | Governance & Decisions | Approve the thesis, guardrails and conditions for target outreach. | Gate 1 approval record | The team needs a common test before it sees attractive targets. | Walk | Critical |  |  | Not Started | All thesis actions | Decision Log tab | Keep
DW-019 | Target Universe | Gate 2 — Target | Targeting & Outreach | Translate the mandate into objective screening criteria. | Target screen | Comparable criteria reduce narrative bias across targets. | Investigate | High |  |  | Not Started | Approved thesis | Acquisition Target Pipeline & Deal Funnel | Keep
DW-020 | Target Universe | Gate 2 — Target | Targeting & Outreach | Build the long list from proprietary, banker and market sources. | Long list with source and date | A broad universe reduces dependence on one auction or one relationship. | Investigate | High |  |  | Not Started | Target screen | Public Company Comps Workbench | Keep
DW-021 | Target Universe | Gate 2 — Target | Strategy & Thesis | Map category leaders, challengers, substitutes and adjacent capabilities. | Market map | Category position matters only when connected to the acquisition thesis. | Investigate | High |  |  | Not Started | Long list | Public Company Comps Workbench | Keep
DW-022 | Target Universe | Gate 2 — Target | Targeting & Outreach | Identify owners, likely control holders and ability to transact. | Ownership and control map | Control and consent should be checked before expensive work begins. | Walk | Critical |  |  | Not Started | Long list |  | Keep
DW-023 | Target Universe | Gate 2 — Target | Financial & Tax | Capture scale, growth, profitability, cash needs and available valuation signals. | Comparable target profile | Initial economics should be based on consistent measures, not headline claims. | Price | High |  |  | Not Started | Long list | Company valuation models | Keep
DW-024 | Target Universe | Gate 2 — Target | Strategy & Thesis | Score each target against the specific capability or market gap. | Short-list rationale | Strategic fit must be explicit enough to test later. | Investigate | High |  |  | Not Started | Market map | Acquisition Target Pipeline & Deal Funnel | Keep
DW-025 | Target Universe | Gate 2 — Target | Operations & Workflows | Flag dependence on founders, licenses, major customers, platforms or partners. | Early dependency flags | Visible dependencies help prioritize outreach questions and diligence. | Protect | High |  |  | Not Started | Target profiles | Due Diligence Checklist | Keep
DW-026 | Target Universe | Gate 2 — Target | Governance & Decisions | Identify auction, proprietary and future-monitoring paths. | Approach strategy by target | Process dynamics affect access, timing and negotiating leverage. | Protect | Medium |  |  | Not Started | Short list |  | Keep
DW-027 | Target Universe | Gate 2 — Target | Strategy & Thesis | Rank targets by thesis fit, transactability, evidence and likely economics. | Ranked short list | Do not let enthusiasm for one target erase alternatives. | Investigate | High |  |  | Not Started | All target work | Acquisition Target Pipeline & Deal Funnel | Keep
DW-028 | Target Universe | Gate 2 — Target | Governance & Decisions | Approve the targets and permitted approach. | Gate 2 approval record | Outreach spends reputation and may create confidentiality or disclosure risk. | Walk | Critical |  |  | Not Started | Ranked short list | Decision Log tab | Keep
DW-029 | First Look & Access | Gate 3 — Access | Targeting & Outreach | Choose who approaches each target and with what message. | Approved outreach plan | The approach should match ownership, motivation and relationship context. | Protect | High |  |  | Not Started | Target approval |  | Keep
DW-030 | First Look & Access | Gate 3 — Access | Targeting & Outreach | Confirm internal code name, access rules and record handling. | Confidentiality protocol | Control sensitive information from first contact. | Protect | High |  |  | Not Started | Target approval |  | Keep
DW-031 | First Look & Access | Gate 3 — Access | Targeting & Outreach | Negotiate confidentiality, use, standstill, non-solicit and clean-team terms as applicable. | Executed NDA | Access terms can restrict later action or create operating risk. | Protect | High |  |  | Not Started | Initial interest |  | Keep
DW-032 | First Look & Access | Gate 3 — Access | Targeting & Outreach | Understand why the seller is considering a transaction now. | Motivation assessment | Seller motivation is data and should be checked against performance and timing. | Investigate | High |  |  | Not Started | Initial discussion | Acquisition Mandate & Target Screen | Keep
DW-033 | First Look & Access | Gate 3 — Access | Targeting & Outreach | Confirm who owns the business and who must approve a transaction. | Preliminary control confirmation | Do not mistake a willing contact for an able seller. | Walk | Critical |  |  | Not Started | Initial discussion |  | Keep
DW-034 | First Look & Access | Gate 3 — Access | Targeting & Outreach | Request the minimum first-look package: CIM or overview, financials, customer mix, employee list and revenue mix. | Minimum information package | An LOI should not be issued from a pitch alone. | Investigate | High |  |  | Not Started | Executed NDA | Due Diligence Checklist | Keep
DW-035 | First Look & Access | Gate 3 — Access | People & Knowledge | Hold a focused first meeting on business model, economics, customers, people and transaction intent. | Meeting notes and follow-up list | Use management access to test claims and identify missing evidence. | Investigate | High |  |  | Not Started | Minimum package | Acquisition Mandate & Target Screen | Keep
DW-036 | First Look & Access | Gate 3 — Access | Governance & Decisions | Record inconsistencies, delayed responses and areas where evidence strengthens confidence. | Evidence and trust log | Trust should update during the process; unknowns remain findings. | Protect | High |  |  | Not Started | Management meeting | Due Diligence Checklist | Keep
DW-037 | First Look & Access | Gate 3 — Access | Targeting & Outreach | Run conflict checks and identify restricted parties or advisors. | Conflict clearance | Avoid compromised advice and late process disruption. | Protect | High |  |  | Not Started | Likely deal team |  | Keep
DW-038 | First Look & Access | Gate 3 — Access | Governance & Decisions | Decide whether the evidence supports deeper access and spending. | Gate 3 approval record | Access is earned by thesis fit, credible ownership and enough evidence to underwrite. | Walk | Critical |  |  | Not Started | First-look assessment | Decision Log tab | Keep
DW-039 | Initial Underwriting | Gate 4 — Economics | Financial & Tax | Rebuild historical revenue and earnings as far as the available records allow. | Preliminary normalized financials | Reported results are not underwritten until they reconcile to operating evidence. | Investigate | High |  |  | Not Started | Minimum information package | Company valuation models | Keep
DW-040 | Initial Underwriting | Gate 4 — Economics | Financial & Tax | Identify adjustments and separate supported, rejected and unresolved add-backs. | Adjustment schedule | An add-back is not value merely because the seller labels it nonrecurring. | Price | Critical |  |  | Not Started | Financial history | Company valuation models | Keep
DW-041 | Initial Underwriting | Gate 4 — Economics | Financing & Cash | Bridge earnings to cash flow, capital expenditure and working-capital needs. | Cash conversion bridge | Price should reflect cash economics and required capital, not EBITDA alone. | Price | Critical |  |  | Not Started | Normalized financials | Company valuation models | Keep
DW-042 | Initial Underwriting | Gate 4 — Economics | Commercial & Customers | Test growth, churn, customer concentration, backlog and pipeline with available evidence. | Preliminary revenue-quality view | Growth receives no credit until its sources and repeatability are understood. | Investigate | High |  |  | Not Started | Customer and revenue data | Due Diligence Checklist | Keep
DW-043 | Initial Underwriting | Gate 4 — Economics | Valuation & Returns | Calculate standalone value using the method appropriate to the business. | Standalone value range | Use normalized EBITDA or free cash flow, SDE for owner-operated businesses, and replacement cost when earnings do not support value. | Price | Critical |  |  | Not Started | Normalized economics | Company valuation models | Keep
DW-044 | Initial Underwriting | Gate 4 — Economics | Valuation & Returns | Bridge enterprise value to equity value, debt, cash, working capital and required investment. | Enterprise-to-equity bridge | The headline price is incomplete without balance-sheet and capital requirements. | Price | Critical |  |  | Not Started | Standalone value | Company valuation models | Keep
DW-045 | Initial Underwriting | Gate 4 — Economics | Integration & Synergies | Build a private buyer-specific synergy case with owners, timing, cost and dependencies. | Preliminary synergy register | Synergy can inform affordability and the private ceiling, but not seller standalone value. | Price | High |  |  | Not Started | Deal thesis | Integration Checklist | Keep
DW-046 | Initial Underwriting | Gate 4 — Economics | Financing & Cash | Test debt capacity, covenants, cash buffer and likely lender requirements. | Financing case | Bankability shapes purchase capacity and certainty. | Price | Critical |  |  | Not Started | Cash conversion and downside | Company valuation models | Keep
DW-047 | Initial Underwriting | Gate 4 — Economics | Strategy & Thesis | Run combined revenue decline and margin compression with delayed synergies. | Best, likely and worst cases | If the worst case is not survivable, the buyer should not advance. | Walk | Critical |  |  | Not Started | Operating model and financing | Company valuation models | Keep
DW-048 | Initial Underwriting | Gate 4 — Economics | Valuation & Returns | Use payback for a strategic buyer and IRR for a financial sponsor, with supporting cash measures. | Buyer return analysis | The return metric must match who is committing the capital. | Price | High |  |  | Not Started | Sources and uses | Company valuation models | Keep
DW-049 | Initial Underwriting | Gate 4 — Economics | Strategy & Thesis | Set the private hard ceiling and walk-away conditions before bidding. | Approved ceiling and conditions | Winning an uneconomic auction is not success. | Walk | Critical |  |  | Not Started | Valuation, financing and downside | Decision Log tab | Keep
DW-050 | Initial Underwriting | Gate 4 — Economics | Governance & Decisions | Approve the indicative posture: advance, investigate, reprice or pass. | Gate 4 approval record | Analysis is incomplete until it changes the buyer's next commitment. | Walk | Critical |  |  | Not Started | Initial underwriting | Decision Log tab | Keep
DW-051 | IOI / LOI | Gate 5 — Exclusivity | Governance & Decisions | Confirm bid instructions, timing, access and competitive dynamics. | Bid requirements summary | A process can change tactics, but it should not change the buyer's economics. | Protect | High |  |  | Not Started | Seller process letter |  | Keep
DW-052 | IOI / LOI | Gate 5 — Exclusivity | Valuation & Returns | Decide whether to give a range or a point price and define assumptions. | Approved indication | A broad non-binding range may preserve access without abandoning the ceiling. | Price | Critical |  |  | Not Started | Gate 4 approval | Company valuation models | Keep
DW-053 | IOI / LOI | Gate 5 — Exclusivity | Legal, Terms & Regulatory | Choose the preferred asset, stock, membership-interest or merger structure. | Preliminary structure memo | Structure allocates liabilities, tax effects, consents and continuity risk. | Protect | High |  |  | Not Started | Legal and tax input |  | Keep
DW-054 | IOI / LOI | Gate 5 — Exclusivity | Valuation & Returns | Define cash, stock, rollover, seller financing, escrow, holdback and earnout concepts. | Consideration outline | Contingency should align payment with results the seller can influence. | Price | High |  |  | Not Started | Financing and seller objectives | Company valuation models | Keep
DW-055 | IOI / LOI | Gate 5 — Exclusivity | Valuation & Returns | State cash-free debt-free treatment, working-capital approach and debt-like items. | Price mechanics summary | Ambiguous mechanics create value transfer at close. | Price | Critical |  |  | Not Started | Enterprise-to-equity bridge | Company valuation models | Keep
DW-056 | IOI / LOI | Gate 5 — Exclusivity | Governance & Decisions | List the evidence and access required during exclusivity. | Diligence access schedule | The LOI should protect the buyer's ability to test the thesis. | Protect | High |  |  | Not Started | Diligence priorities | Due Diligence Checklist | Keep
DW-057 | IOI / LOI | Gate 5 — Exclusivity | Legal, Terms & Regulatory | State key approvals, financing, consents and other conditions to signing or closing. | Conditions outline | Known gates should be explicit before the buyer gives exclusivity value. | Protect | High |  |  | Not Started | Regulatory and financing assessment |  | Keep
DW-058 | IOI / LOI | Gate 5 — Exclusivity | Legal, Terms & Regulatory | Set exclusivity length, extensions, milestones and termination rights. | Exclusivity terms | Time should match the work required and the seller's delivery obligations. | Protect | High |  |  | Not Started | Diligence plan and timeline |  | Keep
DW-059 | IOI / LOI | Gate 5 — Exclusivity | People & Knowledge | Address retention, seller transition and restrictive-covenant principles where appropriate. | People term outline | Value can leave before or at close if key roles are ignored. | Protect | High |  |  | Not Started | Early dependency flags | Integration Checklist | Keep
DW-060 | IOI / LOI | Gate 5 — Exclusivity | Targeting & Outreach | Confirm announcement, disclosure, employee and customer contact restrictions. | Communications restrictions | Premature contact can damage revenue, people and regulatory position. | Protect | High |  |  | Not Started | NDA and counsel input |  | Keep
DW-061 | IOI / LOI | Gate 5 — Exclusivity | Governance & Decisions | Obtain approval for price, ceiling, structure, conditions and exclusivity. | Gate 5 approval record | The LOI fixes core economics without prematurely drafting every agreement term. | Walk | Critical |  |  | Not Started | Final LOI draft | Decision Log tab | Keep
DW-062 | IOI / LOI | Gate 5 — Exclusivity | Integration & Synergies | Sign the LOI and issue a launch package to all workstreams. | Executed LOI and internal launch memo | Every team must understand the thesis, limits and evidence required. | Protect | High |  |  | Not Started | Gate 5 approval | Due Diligence Checklist | Keep
DW-063 | Diligence Mobilization | Gate 6 — Diligence | Integration & Synergies | Translate each thesis condition into a diligence question and evidence request. | Thesis-linked diligence plan | Diligence should prove or disprove the investment case. | Investigate | High |  |  | Not Started | Executed LOI | Due Diligence Checklist | Keep
DW-064 | Diligence Mobilization | Gate 6 — Diligence | Integration & Synergies | Set scope for financial, tax, legal, commercial, operations, people, technology, cyber, insurance and regulatory work. | Workstream scope matrix | The scope should match the target and risks, not a generic list. | Protect | High |  |  | Not Started | Diligence plan | Due Diligence Checklist | Keep
DW-065 | Diligence Mobilization | Gate 6 — Diligence | Targeting & Outreach | Assign one accountable owner and one decision recipient for each workstream. | Diligence RACI | A finding without an owner or recipient is unfinished work. | Protect | High |  |  | Not Started | Scope matrix | Deal Team | Keep
DW-066 | Diligence Mobilization | Gate 6 — Diligence | Targeting & Outreach | Create the request list, index, permissions and update protocol. | Controlled data-room plan | Evidence must be traceable to the claim and current as of a known date. | Protect | High |  |  | Not Started | Scope matrix | Due Diligence Checklist | Keep
DW-067 | Diligence Mobilization | Gate 6 — Diligence | Targeting & Outreach | Set a single Q&A log, routing, response standard and escalation clock. | Q&A protocol | Inconsistent answers across workstreams should be visible and investigated. | Investigate | High |  |  | Not Started | Data-room plan | Due Diligence Checklist | Keep
DW-068 | Diligence Mobilization | Gate 6 — Diligence | Governance & Decisions | Set the categories Investigate, Price, Protect and Walk for material findings. | Issue classification rules | The output of diligence is a decision, not a binder of observations. | Protect | High |  |  | Not Started | Diligence plan | Due Diligence Checklist | Keep
DW-069 | Diligence Mobilization | Gate 6 — Diligence | Operations & Workflows | Identify the revenue, margin, compliance and customer-trust workflows to trace. | Critical workflow list | A buyer acquires the workflows that repeatedly produce results. | Investigate | High |  |  | Not Started | Thesis and process map | Due Diligence Checklist | Keep
DW-070 | Diligence Mobilization | Gate 6 — Diligence | Integration & Synergies | Name an integration lead and begin the integration thesis during diligence. | Integration lead and first thesis draft | Integration planning should start before the agreement is final. | Protect | High |  |  | Not Started | Deal thesis | Integration Checklist | Keep
DW-071 | Diligence Mobilization | Gate 6 — Diligence | Legal, Terms & Regulatory | Have counsel assess antitrust, foreign investment, industry and other filing paths. | Regulatory plan | Required filings and waiting periods can determine timing and certainty. | Protect | High |  |  | Not Started | Structure and market data |  | Keep
DW-072 | Diligence Mobilization | Gate 6 — Diligence | Governance & Decisions | Approve scope, budget, advisors, timetable and reporting cadence. | Gate 6 approval record | The buyer should know what will be tested, by whom, when and for which decision. | Walk | Critical |  |  | Not Started | Mobilization package | Decision Log tab | Keep
DW-073 | Confirmatory Diligence | Gate 7 — Re-underwrite | Financial & Tax | Complete quality-of-earnings work and replicate material financial claims. | Normalized earnings and evidence bridge | Financial statements must tie to the ledger, cash, tax, invoices and contracts. | Price | Critical |  |  | Not Started | Financial data room | Due Diligence Checklist | Keep
DW-074 | Confirmatory Diligence | Gate 7 — Re-underwrite | Commercial & Customers | Validate market, pricing, churn, concentration, pipeline and customer behavior. | Commercial findings and revised forecast | Seller narrative is not enough evidence of demand or defensibility. | Price | Critical |  |  | Not Started | Commercial access | Due Diligence Checklist | Keep
DW-075 | Confirmatory Diligence | Gate 7 — Re-underwrite | Commercial & Customers | Test top customer contracts, relationships, consent needs and change sensitivity. | Customer risk and consent plan | Concentration is more dangerous when tied to one person, contract or event. | Protect | High |  |  | Not Started | Customer data and legal review | Due Diligence Checklist | Keep
DW-076 | Confirmatory Diligence | Gate 7 — Re-underwrite | Operations & Workflows | Walk the workflows that produce revenue, margin, compliance and customer trust. | Workflow transferability map | Observe triggers, inputs, decisions, systems, exceptions, outputs and controls. | Protect | High |  |  | Not Started | Critical workflow list | Due Diligence Checklist | Keep
DW-077 | Confirmatory Diligence | Gate 7 — Re-underwrite | People & Knowledge | Identify actual decision owners, key-person dependence, retention risk and replacement cost. | People and knowledge-transfer plan | Titles can obscure who actually makes the company work. | Protect | High |  |  | Not Started | Management access | Due Diligence Checklist | Keep
DW-078 | Confirmatory Diligence | Gate 7 — Re-underwrite | Technology & Data | Assess systems, architecture, technical debt, access, contracts and separation needs. | Technology risk and transition plan | Technology gaps can require capital or interrupt customer delivery. | Price | High |  |  | Not Started | Technology access | Due Diligence Checklist | Keep
DW-079 | Confirmatory Diligence | Gate 7 — Re-underwrite | Technology & Data | Review incidents, controls, privacy, data rights, AI use and remediation needs. | Cyber, privacy and data-rights findings | A documented workflow is not transferable or licensable unless the rights are clean. | Protect | High |  |  | Not Started | System and contract access | Due Diligence Checklist | Keep
DW-080 | Confirmatory Diligence | Gate 7 — Re-underwrite | Legal, Terms & Regulatory | Review capitalization, entities, contracts, disputes, IP, compliance and permits. | Legal issues and protection plan | Legal findings should change structure, conditions, price or protection. | Protect | High |  |  | Not Started | Legal data room | Due Diligence Checklist | Keep
DW-081 | Confirmatory Diligence | Gate 7 — Re-underwrite | Financial & Tax | Assess exposures, attributes, structure and post-close compliance requirements. | Tax findings and structure recommendation | Tax affects after-tax value, liability transfer and closing mechanics. | Price | Critical |  |  | Not Started | Tax records | Due Diligence Checklist | Keep
DW-082 | Confirmatory Diligence | Gate 7 — Re-underwrite | Legal, Terms & Regulatory | Confirm filings, approvals, remedies, timing and clean-team rules. | Regulatory status and conduct protocol | The parties must not close before required waiting periods or operate as one before closing. | Protect | High |  |  | Not Started | Counsel assessment |  | Keep
DW-083 | Confirmatory Diligence | Gate 7 — Re-underwrite | Governance & Decisions | Assess contradictions or suspected misrepresentation by type, severity, materiality and explanation. | Integrity finding and response | Intentional conduct matters, but the decision should follow the evidence and consequence. | Walk | Critical |  |  | Not Started | Evidence and trust log | Due Diligence Checklist | Keep
DW-084 | Confirmatory Diligence | Gate 7 — Re-underwrite | Integration & Synergies | Rebuild each synergy from a baseline, action, owner, timing, cost and dependency. | Underwritten synergy register | Top-down percentages are not underwritable. | Price | High |  |  | Not Started | Diligence findings | Integration Checklist | Keep
DW-085 | Confirmatory Diligence | Gate 7 — Re-underwrite | Integration & Synergies | Quantify churn, talent loss, stranded cost, transition cost and delayed value. | Dis-synergy register | Gross benefits without transition losses overstate value. | Price | Critical |  |  | Not Started | Workstream findings | Integration Checklist | Keep
DW-086 | Confirmatory Diligence | Gate 7 — Re-underwrite | Integration & Synergies | Convert material findings into Day 1, retention, consent, TSA and integration actions. | Diligence-to-integration handoff | No material issue should disappear between the deal team and operators. | Protect | High |  |  | Not Started | Issue log | Integration Checklist | Keep
DW-087 | Confirmatory Diligence | Gate 7 — Re-underwrite | Governance & Decisions | Re-underwrite the thesis, price, ceiling, downside and transferability from evidence. | Gate 7 investment case | Momentum is not evidence. The deal must still work at the current terms. | Walk | Critical |  |  | Not Started | All diligence findings | Company valuation models | Keep
DW-088 | Structure & Negotiation | Gate 7 — Re-underwrite | Legal, Terms & Regulatory | Confirm the form of transaction after diligence and tax analysis. | Final structure recommendation | Structure should reflect identified liabilities, transfer needs and continuity. | Protect | High |  |  | Not Started | Diligence findings |  | Keep
DW-089 | Structure & Negotiation | Gate 7 — Re-underwrite | Valuation & Returns | Update standalone value and the enterprise-to-equity bridge. | Final valuation bridge | Diligence adjustments must reach the price mechanics. | Price | Critical |  |  | Not Started | Re-underwriting | Company valuation models | Keep
DW-090 | Structure & Negotiation | Gate 7 — Re-underwrite | Financing & Cash | Set the peg, definitions, exclusions, sample calculation and dispute method. | Agreed working-capital exhibit | Vague definitions create post-close value leakage. | Price | Critical |  |  | Not Started | Historical working capital | Company valuation models | Keep
DW-091 | Structure & Negotiation | Gate 7 — Re-underwrite | Financing & Cash | Define cash, indebtedness, debt-like items and payoff mechanics. | Agreed debt and cash schedule | The equity check must reflect what is delivered and assumed. | Price | Critical |  |  | Not Started | Debt schedule | Company valuation models | Keep
DW-092 | Structure & Negotiation | Gate 7 — Re-underwrite | Legal, Terms & Regulatory | Use an earnout only when the seller can influence a clearly defined result. | Earnout model and sample calculations | Ambiguous metrics or lost seller control create disputes. | Protect | High |  |  | Not Started | Seller role and forecast | Company valuation models | Keep
DW-093 | Structure & Negotiation | Gate 7 — Re-underwrite | Legal, Terms & Regulatory | Map findings to covenants, conditions, representations, indemnity, escrow or insurance. | Issue-to-agreement matrix | Legal drafting should express the economic decision already made. | Protect | High |  |  | Not Started | Diligence issue log | Due Diligence Checklist | Keep
DW-094 | Structure & Negotiation | Gate 7 — Re-underwrite | Legal, Terms & Regulatory | List contract, lender, landlord, regulatory and third-party consents with owners. | Consent tracker | Nontransferable rights can break the operating perimeter. | Protect | High |  |  | Not Started | Contract and regulatory review | Integration Checklist | Keep
DW-095 | Structure & Negotiation | Gate 7 — Re-underwrite | People & Knowledge | Finalize retention, transition, employment and restrictive-covenant arrangements. | People agreements | The buyer must protect the people and knowledge required to operate. | Protect | High |  |  | Not Started | People diligence | Integration Checklist | Keep
DW-096 | Structure & Negotiation | Gate 7 — Re-underwrite | Operations & Workflows | Define services, levels, volume, pricing, term, exit and escalation. | TSA schedule | Transition support needs a measurable exit path, not a vague promise. | Protect | High |  |  | Not Started | Separation assessment | Integration Checklist | Keep
DW-097 | Structure & Negotiation | Gate 7 — Re-underwrite | Legal, Terms & Regulatory | Set ordinary-course covenants and required consent for material actions. | Interim operating covenants | The target must preserve value without giving the buyer premature control. | Protect | High |  |  | Not Started | Counsel and operating input |  | Keep
DW-098 | Structure & Negotiation | Gate 7 — Re-underwrite | Legal, Terms & Regulatory | Review disclosure schedules against diligence findings and agreement terms. | Complete disclosure schedules | Disclosure should not silently neutralize the protections the buyer underwrote. | Protect | High |  |  | Not Started | Near-final agreement | Due Diligence Checklist | Keep
DW-099 | Structure & Negotiation | Gate 7 — Re-underwrite | Financing & Cash | Build sources, uses, fees, payoffs, escrows and minimum cash. | Draft funds-flow memorandum | Closing must be operationally and financially executable. | Protect | High |  |  | Not Started | Financing and agreement | Company valuation models | Keep
DW-100 | Structure & Negotiation | Gate 7 — Re-underwrite | Legal, Terms & Regulatory | Track open economic points against the ceiling and walk-away conditions. | Open-points list with authority | Each concession should have a known value and approver. | Walk | Critical |  |  | Not Started | All negotiation drafts | Decision Log tab | Keep
DW-101 | Approval & Signing | Gate 8 — Signing approval | Strategy & Thesis | Prepare the final decision memo with thesis, evidence, price, returns, risks and integration plan. | Final investment memo | Decision-makers need one integrated view, not separate advisor binders. | Walk | Critical |  |  | Not Started | Re-underwriting and final terms |  | Keep
DW-102 | Approval & Signing | Gate 8 — Signing approval | Strategy & Thesis | Show the combined downside, liquidity, covenant headroom and response actions. | Final downside case | The transaction still must be survivable at signing. | Walk | Critical |  |  | Not Started | Final financing terms | Company valuation models | Keep
DW-103 | Approval & Signing | Gate 8 — Signing approval | Governance & Decisions | List all unresolved information and the consequence of each. | Open uncertainty schedule | Unknowns do not become zero risk because the signing date is near. | Investigate | High |  |  | Not Started | Issue log | Due Diligence Checklist | Keep
DW-104 | Approval & Signing | Gate 8 — Signing approval | Legal, Terms & Regulatory | Compare final economics with the approved ceiling and prior indications. | Terms bridge | Price drift and risk-transfer changes should be explicit. | Price | Critical |  |  | Not Started | Final agreement | Company valuation models | Keep
DW-105 | Approval & Signing | Gate 8 — Signing approval | Financing & Cash | Obtain committed financing, approvals and conditions consistent with the agreement. | Financing commitment package | Unmatched conditions can create closing failure or buyer liability. | Protect | High |  |  | Not Started | Final sources and uses |  | Keep
DW-106 | Approval & Signing | Gate 8 — Signing approval | Legal, Terms & Regulatory | Confirm agreement, disclosure schedules and ancillary documents are execution-ready. | Legal signoff package | Unresolved drafting can change the approved economics or protections. | Protect | High |  |  | Not Started | Final documents |  | Keep
DW-107 | Approval & Signing | Gate 8 — Signing approval | Legal, Terms & Regulatory | Confirm filing strategy, interim conduct and expected closing path. | Regulatory signoff | Regulatory timing and remedies affect certainty and value. | Protect | High |  |  | Not Started | Counsel plan |  | Keep
DW-108 | Approval & Signing | Gate 8 — Signing approval | Integration & Synergies | Approve the integration thesis, Day 1 scope, leaders, budget and critical actions. | Integration approval package | The buyer should know how value and continuity will be managed before signing. | Protect | High |  |  | Not Started | Diligence handoff | Integration Checklist | Keep
DW-109 | Approval & Signing | Gate 8 — Signing approval | Governance & Decisions | Obtain required management, investment committee and board approvals. | Gate 8 approval record | Approvals should reflect the final terms and current evidence. | Walk | Critical |  |  | Not Started | Final decision package | Decision Log tab | Keep
DW-110 | Approval & Signing | Gate 8 — Signing approval | Governance & Decisions | Approve announcement, employee, customer, vendor and lender messaging. | Signing communications plan | Early messages should protect people and revenue without promising unready changes. | Protect | High |  |  | Not Started | Legal and integration input | Integration Checklist | Keep
DW-111 | Approval & Signing | Gate 8 — Signing approval | Integration & Synergies | Run signature and release mechanics with a single closing coordinator. | Executed transaction documents | Document control prevents inconsistent versions and missing signatures. | Protect | High |  |  | Not Started | All approvals |  | Keep
DW-112 | Approval & Signing | Gate 8 — Signing approval | Integration & Synergies | Issue the signed-deal summary, obligations calendar and closing plan. | Signed-deal handoff package | Operators need the actual commitments, not only the deal team's memory. | Protect | High |  |  | Not Started | Signing complete | Integration Checklist | Keep
DW-113 | Sign-to-Close | Gate 9 — Closing conditions | Governance & Decisions | Stand up the integration management office and workstream cadence. | Active governance calendar | Clear decision rights and escalation keep dependencies visible. | Protect | High |  |  | Not Started | Signed-deal handoff | Integration Checklist | Keep
DW-114 | Sign-to-Close | Gate 9 — Closing conditions | Legal, Terms & Regulatory | Submit required filings and track requests, remedies and waiting periods. | Regulatory tracker | The parties cannot close until required conditions are satisfied. | Protect | High |  |  | Not Started | Signed agreement |  | Keep
DW-115 | Sign-to-Close | Gate 9 — Closing conditions | Targeting & Outreach | Control competitively sensitive information and approved pre-close planning. | Clean-team protocol and access log | Planning must remain separate from premature operating control. | Protect | High |  |  | Not Started | Counsel instructions |  | Keep
DW-116 | Sign-to-Close | Gate 9 — Closing conditions | Legal, Terms & Regulatory | Secure required customer, vendor, lender, landlord, license and partner consents. | Executed consent package | Missing consent can strand revenue, systems or operating rights. | Protect | High |  |  | Not Started | Consent tracker | Integration Checklist | Keep
DW-117 | Sign-to-Close | Gate 9 — Closing conditions | People & Knowledge | Make permitted leadership, retention and transition preparations. | People readiness plan | Uncertainty can cause avoidable loss of talent and relationships. | Protect | High |  |  | Not Started | People agreements | Integration Checklist | Keep
DW-118 | Sign-to-Close | Gate 9 — Closing conditions | Operations & Workflows | List the transactions that must work on Day 1: service, shipping, billing, cash, payroll and compliance. | Critical-event map | Day 1 means control and continuity, not complete integration. | Protect | High |  |  | Not Started | Workflow diligence | Integration Checklist | Keep
DW-119 | Sign-to-Close | Gate 9 — Closing conditions | Technology & Data | Dry-run critical workflows, system access, authority and escalation. | Simulation results and resolved gaps | A plan is not ready until the people and systems can execute it. | Protect | High |  |  | Not Started | Critical-event map | Integration Checklist | Keep
DW-120 | Sign-to-Close | Gate 9 — Closing conditions | Financial & Tax | Finalize funds flow, bank accounts, signing authority, purchase accounting data and close calendar. | Finance closing package | Cash and control must work immediately after close. | Protect | High |  |  | Not Started | Final debt and funds flow | Integration Checklist | Keep
DW-121 | Sign-to-Close | Gate 9 — Closing conditions | Governance & Decisions | Sequence messages and prepare approved Q&A for every stakeholder group. | Day 1 communications package | The wrong message or timing can damage customers and employees. | Protect | High |  |  | Not Started | Closing date and legal clearance | Integration Checklist | Keep
DW-122 | Sign-to-Close | Gate 9 — Closing conditions | Integration & Synergies | Lock baselines, owners, timing, costs, dependencies and measurement methods. | Approved synergy register | Announcements and headcount actions are not realized value. | Price | High |  |  | Not Started | Final operating data | Integration Checklist | Keep
DW-123 | Sign-to-Close | Gate 9 — Closing conditions | Operations & Workflows | Review every closing condition, obligation, approval and Day 1 checkpoint. | Closing readiness dashboard | Final momentum must not override a failed condition or walk-away rule. | Walk | Critical |  |  | Not Started | All sign-to-close work | Integration Checklist | Keep
DW-124 | Sign-to-Close | Gate 9 — Closing conditions | Governance & Decisions | Approve closing only after the legal, financial and operating gates are satisfied. | Gate 9 approval record | Closing is the next irreversible commitment. | Walk | Critical |  |  | Not Started | Closing readiness dashboard | Decision Log tab | Keep
DW-125 | Closing & Day 1 | Gate 10 — Day 1 | Legal, Terms & Regulatory | Confirm signatures, funds, releases, payoffs, certificates and effective time. | Completed closing checklist | Control should transfer only when all required mechanics are complete. | Protect | High |  |  | Not Started | Gate 9 approval |  | Keep
DW-126 | Closing & Day 1 | Gate 10 — Day 1 | Legal, Terms & Regulatory | Implement boards, officers, authority, bank mandates and reserved matters. | Legal control confirmation | The buyer needs clear authority without interrupting ordinary work. | Protect | High |  |  | Not Started | Closing effective | Integration Checklist | Keep
DW-127 | Closing & Day 1 | Gate 10 — Day 1 | People & Knowledge | Deliver communications, manager guidance, payroll, benefits and access support. | Employee readiness confirmation | Employees need to know what changes now, what does not and where to get help. | Protect | High |  |  | Not Started | Closing effective | Integration Checklist | Keep
DW-128 | Closing & Day 1 | Gate 10 — Day 1 | Commercial & Customers | Contact priority customers, confirm service continuity and monitor reactions. | Customer contact and issue log | Protect existing revenue before pursuing new cross-sell. | Protect | High |  |  | Not Started | Customer coverage plan | Integration Checklist | Keep
DW-129 | Closing & Day 1 | Gate 10 — Day 1 | Operations & Workflows | Monitor order, service, delivery, support, billing and collection events. | Live continuity dashboard | The buyer should see failures quickly and assign a response owner. | Protect | High |  |  | Not Started | Critical-event map | Integration Checklist | Keep
DW-130 | Closing & Day 1 | Gate 10 — Day 1 | Technology & Data | Activate identity, email, critical systems, privileged access and support. | Technology readiness confirmation | Access failures can stop work even when the legal close succeeded. | Protect | High |  |  | Not Started | System simulations | Integration Checklist | Keep
DW-131 | Closing & Day 1 | Gate 10 — Day 1 | Technology & Data | Confirm monitoring, incident response, backups and administrator control. | Security control confirmation | The ownership transition can create a period of elevated vulnerability. | Protect | High |  |  | Not Started | Cyber plan | Integration Checklist | Keep
DW-132 | Closing & Day 1 | Gate 10 — Day 1 | Financial & Tax | Run invoicing, cash receipts, purchasing, payments, payroll and close procedures. | Finance continuity confirmation | Cash operations must work from the first day. | Protect | High |  |  | Not Started | Finance closing package | Integration Checklist | Keep
DW-133 | Closing & Day 1 | Gate 10 — Day 1 | Legal, Terms & Regulatory | Confirm permits, reporting, responsible officers and required notices. | Compliance readiness confirmation | Regulatory obligations continue through the ownership change. | Protect | High |  |  | Not Started | Regulatory plan | Integration Checklist | Keep
DW-134 | Closing & Day 1 | Gate 10 — Day 1 | Operations & Workflows | Open the issue log, daily cadence and executive escalation channel. | Active Day 1 command center | Critical issues need immediate ownership and decision rights. | Protect | High |  |  | Not Started | IMO governance | Integration Checklist | Keep
DW-135 | Closing & Day 1 | Gate 10 — Day 1 | Governance & Decisions | Correct inaccurate messages and recurring questions quickly. | Updated Q&A and issue themes | Silence lets uncertainty spread among customers and employees. | Protect | High |  |  | Not Started | Stakeholder feedback | Integration Checklist | Keep
DW-136 | Closing & Day 1 | Gate 10 — Day 1 | Governance & Decisions | Confirm control and continuity before broad integration changes begin. | Gate 10 readiness record | Stabilize the acquired business before redesigning it. | Walk | Critical |  |  | Not Started | Day 1 confirmations | Decision Log tab | Keep
DW-137 | First 100 Days | Gate 11 — Value delivery | Integration & Synergies | Compare actual revenue, margin, cash and customer signals with the deal case. | 30-day thesis update | Early operating evidence should update the investment case. | Investigate | High |  |  | Not Started | Day 1 baseline | Integration Checklist | Keep
DW-138 | First 100 Days | Gate 11 — Value delivery | Commercial & Customers | Track priority accounts, renewals, churn, usage, pipeline and collections. | Revenue continuity dashboard | Revenue-producing functions should change carefully and with evidence. | Protect | High |  |  | Not Started | Customer data feeds | Integration Checklist | Keep
DW-139 | First 100 Days | Gate 11 — Value delivery | People & Knowledge | Confirm retention, leadership decisions, knowledge transfer and backup coverage. | People continuity dashboard | Key knowledge and relationships must move from individuals into the organization. | Protect | High |  |  | Not Started | People readiness plan | Integration Checklist | Keep
DW-140 | First 100 Days | Gate 11 — Value delivery | Operations & Workflows | Assign Preserve, Protect, Combine, Standardize or Retire to critical workflows. | Workflow decision map | Change each workflow according to the source of value and the evidence. | Protect | High |  |  | Not Started | Workflow transferability map | Integration Checklist | Keep
DW-141 | First 100 Days | Gate 11 — Value delivery | Operations & Workflows | Integrate finance, HR, technology and support functions when continuity tests pass. | Approved transition waves | Cost functions can usually move faster than revenue functions. | Protect | High |  |  | Not Started | Day 1 stability | Integration Checklist | Keep
DW-142 | First 100 Days | Gate 11 — Value delivery | Financial & Tax | Maintain a standalone operating view for up to six months when useful. | Comparable standalone reporting | Temporary visibility helps distinguish acquired performance from synergy and integration effects. | Protect | High |  |  | Not Started | Finance data and earnout needs | Integration Checklist | Keep
DW-143 | First 100 Days | Gate 11 — Value delivery | Integration & Synergies | Track actions, realized results, one-time costs and revenue effects separately. | Monthly synergy report | Realized value requires evidence, not announcement. | Price | High |  |  | Not Started | Locked synergy baselines | Integration Checklist | Keep
DW-144 | First 100 Days | Gate 11 — Value delivery | Governance & Decisions | Approve, delay or stop major integration moves based on observed results. | 30-, 60- and 100-day decision records | The plan should change when the evidence changes. | Protect | High |  |  | Not Started | Performance dashboard | Decision Log tab | Keep
DW-145 | First 100 Days | Gate 11 — Value delivery | Technology & Data | Use pilots, parallel runs, acceptance criteria and rollback plans for cutovers. | Cutover approval package | System changes should not put customers, cash or compliance at unnecessary risk. | Protect | High |  |  | Not Started | Stable workflows | Integration Checklist | Keep
DW-146 | First 100 Days | Gate 11 — Value delivery | Operations & Workflows | Track service levels, consumption, exit milestones and hidden manual support. | TSA exit dashboard | A TSA should end through tested replacement, not deadline pressure. | Protect | High |  |  | Not Started | TSA schedule | Integration Checklist | Keep
DW-147 | First 100 Days | Gate 11 — Value delivery | Valuation & Returns | Reforecast the deal case honestly from actual results and remaining actions. | 100-day reforecast | Do not preserve an obsolete acquisition case after reality changes. | Price | Critical |  |  | Not Started | Actual performance and synergy data | Company valuation models | Keep
DW-148 | First 100 Days | Gate 11 — Value delivery | Governance & Decisions | Confirm the operating model and transfer ongoing actions to accountable leaders. | Gate 11 approval record | The integration program should hand off work without losing ownership. | Protect | High |  |  | Not Started | 100-day review | Decision Log tab | Keep
DW-149 | Post-Close Review | Gate 12 — Lessons | Valuation & Returns | Compare the original thesis with standalone performance, synergies, dis-synergies and total investment. | Post-close value review | Judge the acquisition against what was underwritten, not against a revised story. | Investigate | High |  |  | Not Started | Stable operating data | Company valuation models | Keep
DW-150 | Post-Close Review | Gate 12 — Lessons | Valuation & Returns | Compare forecast assumptions with actual revenue, margin, cash, timing and capital needs. | Forecast variance analysis | Recurring bias should change future underwriting methods. | Investigate | High |  |  | Not Started | Post-close actuals | Company valuation models | Keep
DW-151 | Post-Close Review | Gate 12 — Lessons | Governance & Decisions | Identify which findings were predictive, missed or overstated. | Diligence effectiveness review | The team should improve scope and evidence standards from actual outcomes. | Investigate | High |  |  | Not Started | Issue log and results | Due Diligence Checklist | Keep
DW-152 | Post-Close Review | Gate 12 — Lessons | Governance & Decisions | Review time, fees, advisor performance, governance and decision quality. | Process review | Speed and cost matter, but should not be confused with decision quality. | Protect | Medium |  |  | Not Started | Deal records |  | Keep
DW-153 | Post-Close Review | Gate 12 — Lessons | Integration & Synergies | Assess continuity, people, systems, workflows, TSA exits and customer effects. | Integration outcome review | A deal is not complete when the documents are signed. | Protect | High |  |  | Not Started | Integration dashboards | Integration Checklist | Keep
DW-154 | Post-Close Review | Gate 12 — Lessons | People & Knowledge | Record the judgments that should change the next target screen, LOI or diligence plan. | Lessons and doctrine updates | Institutional memory should improve the next acquisition. | Investigate | High |  |  | Not Started | All post-close reviews |  | Keep
DW-155 | Post-Close Review | Gate 12 — Lessons | Governance & Decisions | Preserve approved models, decisions, evidence indexes and final documents with access controls. | Complete deal archive | A usable record supports audits, earnouts, claims and future learning. | Protect | High |  |  | Not Started | Closeout records |  | Keep
DW-156 | Post-Close Review | Gate 12 — Lessons | Governance & Decisions | Close the deal program only after residual actions have operating owners. | Gate 12 closeout record | Program closure should not orphan remaining obligations or risks. | Protect | High |  |  | Not Started | Residual action list | Decision Log tab | Keep

## Stage Gates
M&A Decision Gates
Advance only when the required evidence supports the next commitment. A gate can be held without forcing a yes or no.
Gate | Decision | Decision question | Required evidence | Decision authority | Advance | Hold / rework | Walk indicator | Status | Scope decision | Reviewer notes
Gate 0 | Mandate approved | Is acquisition the right path, and are authority, capital and risk limits clear? | Mandate; capital envelope; governance map; risk guardrails | Executive sponsor / board as required | Begin thesis and target work | Clarify strategy, resources or authority | M&A is the default answer without a defined problem | Not Started | Keep
Gate 1 | Thesis approved | What must be true, what transfers, and what is the private valuation discipline? | Acquisition thesis; guardrails; downside test; hard-ceiling method | Executive sponsor / investment committee | Build target universe | Revise thesis or evidence tests | No survivable downside or no transferable source of value | Not Started | Keep
Gate 2 | Target approved | Does the target fit the thesis, and can the seller plausibly deliver control? | Target screen; ownership map; initial economics; approach plan | Deal sponsor | Authorize outreach | Keep monitoring or refine target profile | No control path, no thesis fit or prohibited exposure | Not Started | Keep
Gate 3 | Access approved | Is there enough credible information and seller alignment to spend more? | NDA; minimum information package; management assessment; trust log | Deal sponsor | Begin initial underwriting | Request missing information | Seller cannot transact or withholds minimum evidence | Not Started | Keep
Gate 4 | Economics approved | Do standalone value, financing and the combined downside support a bid? | Normalized economics; valuation range; financing case; hard ceiling | Investment committee / delegated authority | Prepare indication or LOI | Investigate or reprice | Price exceeds ceiling or worst case is not survivable | Not Started | Keep
Gate 5 | Exclusivity approved | Are core economics, structure, access and conditions clear enough for an LOI? | Approved LOI; price mechanics; diligence access; conditions; exclusivity | Authorized signatories | Execute LOI and launch diligence | Revise terms | LOI leaves core economics or required access unresolved | Not Started | Keep
Gate 6 | Diligence launched | Will the work test the thesis and send findings to a decision owner? | Workstream scope; RACI; data room; Q&A; issue rules; timetable | Deal lead / steering committee | Run confirmatory diligence | Fix scope, ownership or evidence access | No owner, no usable evidence path or no decision cadence | Not Started | Keep
Gate 7 | Re-underwriting approved | Does the deal still work after diligence and negotiation? | Updated valuation; downside; findings; agreement map; integration plan | Investment committee / board as required | Finalize documents and approval | Investigate, reprice or restructure | Thesis breaks, transfer fails, integrity fails or price exceeds ceiling | Not Started | Keep
Gate 8 | Signing approved | Do final terms match the approved economics, protections and integration plan? | Final decision memo; documents; financing; regulatory and integration signoffs | Board / investment committee / signatories | Sign transaction | Resolve conditions or revise approval | Approval relies on stale terms or unresolved critical unknowns | Not Started | Keep
Gate 9 | Closing approved | Are all legal, financial, regulatory and operating closing conditions satisfied? | Closing checklist; funds flow; consents; regulatory clearance; Day 1 readiness | Authorized closing committee | Release signatures and funds | Hold closing | Required condition, funding or Day 1 control is not ready | Not Started | Keep
Gate 10 | Day 1 stable | Can the business operate, serve customers, pay people and control cash? | Control, customer, people, operations, technology, cyber, finance and compliance signoffs | Executive sponsor / integration leader | Begin sequenced integration | Stabilize before broader change | Critical customer, cash, people, system or compliance failure | Not Started | Keep
Gate 11 | Value delivery confirmed | Do actual results support the operating model and next integration decisions? | 30/60/100-day reviews; workflow decisions; synergy results; reforecast | Executive sponsor / business leaders | Transfer to normal operations | Delay or stop unsupported changes | Revenue or continuity is deteriorating without corrective action | Not Started | Keep
Gate 12 | Program closed | Have results been compared with the original thesis and all residual actions assigned? | Value review; lessons; archive; residual action owners | Executive sponsor / board as required | Close program and update doctrine | Keep program open | Unowned obligations, risks or lessons remain | Not Started | Keep

## Deal Team
Deal Team & Decision Ownership
Name accountable owners for the work and the decision. Advisors can support judgment but should not own the acquisition thesis.
Role | Purpose | Active phases | Core responsibilities | Named owner | Backup / advisor | Scope decision | Reviewer notes
Executive sponsor | Owns the acquisition thesis, resolves senior conflicts and remains accountable for the outcome. | Mandate through post-close | Gate decisions; leadership alignment; resources |  |  | Keep
Corporate development / deal lead | Runs the process, integrates workstreams and keeps the decision case current. | Mandate through closing | Process plan; valuation; approvals; negotiation; issue integration |  |  | Keep
Business sponsor | Defines strategic need and owns operating results after close. | Thesis through post-close | Commercial fit; management access; integration priorities |  |  | Keep
Finance | Rebuilds economics, cash, working capital, purchase price and post-close reporting. | First look through post-close | Valuation; financing; funds flow; purchase accounting; performance |  |  | Keep
Legal | Owns transaction documents, corporate authority, contracts, consents and legal risk allocation. | Outreach through closing | NDA; structure; agreement; disclosure; closing documents |  |  | Keep
Tax | Tests exposure and attributes and advises on structure and post-close requirements. | Initial underwriting through closing | Tax diligence; structure; purchase price allocation inputs |  |  | Keep
Commercial / sales | Tests market and revenue quality and protects customer continuity. | First look through integration | Market; customers; pipeline; pricing; account coverage |  |  | Keep
Operations | Tests how the company actually delivers and owns workflow continuity. | Diligence through integration | Process walks; capacity; vendors; service delivery; controls |  |  | Keep
People / HR | Tests leadership, retention, compensation, benefits and organizational requirements. | Diligence through integration | People diligence; retention; communications; organization design |  |  | Keep
Technology / cyber / data | Tests systems, security, data rights and transition feasibility. | Diligence through integration | Architecture; access; cyber; privacy; data; cutover |  |  | Keep
Regulatory / compliance | Assesses filings, licenses, conduct rules and ongoing obligations. | Target screen through closing | Regulatory path; clean teams; permits; reporting |  |  | Keep
Integration leader | Turns the deal thesis and diligence findings into sequenced operating action. | Diligence through post-close | Integration thesis; Day 1; workstreams; dependencies; value tracking |  |  | Keep
External advisors | Provide specialized transaction, legal, accounting, tax, commercial or technical work. | As required | Defined scope; evidence; conclusions; conflicts and incentives disclosed |  |  | Keep

## Decision Log
Deal Decision Log
Record material decisions, the evidence considered, the limits accepted and the next accountable action.
Decision ID | Date | Phase / gate | Decision | Evidence considered | Options | Decision owner | Outcome | Conditions / limits | Next action | Action owner | Due date | Status | Scope decision
DEC-001 | [11 empty] | Open | Keep
DEC-002 | [11 empty] | Open | Keep
DEC-003 | [11 empty] | Open | Keep
DEC-004 | [11 empty] | Open | Keep
DEC-005 | [11 empty] | Open | Keep
DEC-006 | [11 empty] | Open | Keep
DEC-007 | [11 empty] | Open | Keep
DEC-008 | [11 empty] | Open | Keep
DEC-009 | [11 empty] | Open | Keep
DEC-010 | [11 empty] | Open | Keep
DEC-011 | [11 empty] | Open | Keep
DEC-012 | [11 empty] | Open | Keep
DEC-013 | [11 empty] | Open | Keep
DEC-014 | [11 empty] | Open | Keep
DEC-015 | [11 empty] | Open | Keep
DEC-016 | [11 empty] | Open | Keep
DEC-017 | [11 empty] | Open | Keep
DEC-018 | [11 empty] | Open | Keep
DEC-019 | [11 empty] | Open | Keep
DEC-020 | [11 empty] | Open | Keep
DEC-021 | [11 empty] | Open | Keep
DEC-022 | [11 empty] | Open | Keep
DEC-023 | [11 empty] | Open | Keep
DEC-024 | [11 empty] | Open | Keep
DEC-025 | [11 empty] | Open | Keep
DEC-026 | [11 empty] | Open | Keep
DEC-027 | [11 empty] | Open | Keep
DEC-028 | [11 empty] | Open | Keep
DEC-029 | [11 empty] | Open | Keep
DEC-030 | [11 empty] | Open | Keep
DEC-031 | [11 empty] | Open | Keep
DEC-032 | [11 empty] | Open | Keep
DEC-033 | [11 empty] | Open | Keep
DEC-034 | [11 empty] | Open | Keep
DEC-035 | [11 empty] | Open | Keep
DEC-036 | [11 empty] | Open | Keep
DEC-037 | [11 empty] | Open | Keep
DEC-038 | [11 empty] | Open | Keep
DEC-039 | [11 empty] | Open | Keep
DEC-040 | [11 empty] | Open | Keep
DEC-041 | [11 empty] | Open | Keep
DEC-042 | [11 empty] | Open | Keep
DEC-043 | [11 empty] | Open | Keep
DEC-044 | [11 empty] | Open | Keep
DEC-045 | [11 empty] | Open | Keep
DEC-046 | [11 empty] | Open | Keep
DEC-047 | [11 empty] | Open | Keep
DEC-048 | [11 empty] | Open | Keep
DEC-049 | [11 empty] | Open | Keep
DEC-050 | [11 empty] | Open | Keep