## Dashboard
MikeYe.com Post-Deal Integration Checklist
Version 1.1 · November 2026 · 104 integration actions, 12 Day 1 gates, 14 workflow decisions, a synergy register and a risk log.
How to use | Clear the Day 1 gates first. Then work the Integration Plan by phase: owner and date on every action, and no change to a working process until its evidence is in. Set Reviewer decision to Remove for actions that don't apply; they drop out of the counts.
Rule | Protect revenue while integrating cost. Count a saving only once the old cost has stopped and the new running cost is in.
Day 1 | Now | What it tells you
Day 1 verdict | Not ready: 12 gates open | Every in-scope gate on the Day 1 tab must read Ready.
Gates ready | 0 of 12 | Legal control, cash, payroll, customers, systems and the rest.
Gates blocked | 0 | Fix or escalate before close.
Integration plan | Now | What it tells you
Actions in scope | 104 | Actions still in play.
Complete | 0 | Done, with the evidence in the Ready column.
% complete | 0% | Share of in-scope actions done.
Blocked | 0 | Stuck. Name the fix or escalate.
Overdue | 0 | Past the target date and not done.
Open Critical actions with no owner | 57 | Assign these first.
Open High revenue-impact actions | 76 | Where customers or revenue could be hurt. Go slow here.
Synergies | Amount | What it tells you
Underwritten annual benefit | 0 | Net of dis-synergies, from the Synergies tab.
Realized run-rate to date | 0 | Count only savings where the old cost has actually stopped.
% realized | 0% | Realized run-rate against what was underwritten.
One-time cost to achieve | 0 | Total cost to deliver the synergies.
Risks and decisions | Open | What it tells you
Open issues | 0 | Logged on the Risks & Decisions tab.
Critical severity | 0 | Open issues rated Critical.
Escalated | 0 | Waiting on a decision above the integration lead.
Overdue | 0 | Past due and still open.
Progress by phase | Actions | Complete | Blocked | % complete
Diligence | 12 | 0 | 0 | 0%
Sign-to-Close | 25 | 0 | 0 | 0%
Day 1 | 17 | 0 | 0 | 0%
Days 2-30 | 17 | 0 | 0 | 0%
Days 31-60 | 14 | 0 | 0 | 0%
Days 61-100 | 13 | 0 | 0 | 0%
Post-100 | 6 | 0 | 0 | 0%
Disposition | Meaning
Preserve | Keep a proven workflow running as-is while the buyer learns.
Protect | Add redundancy, rights, controls or retention around fragile value.
Combine | Join complementary capabilities only when the value and dependencies are clear.
Standardize | Move to a common process where the evidence supports it.
Retire | Remove duplication only after continuity, migration and rollback are proven.
Formulas:
Now = COUNTIFS(IntegrationPlanTable[Target date],"<"&TODAY(),IntegrationPlanTable[Status],"<>Complete",IntegrationPlanTable[Status],"<>N/A",IntegrationPlanTable[Reviewer decision],"<>Remove")
Now = COUNTIFS(IntegrationRiskTable[Due date],"<"&TODAY(),IntegrationRiskTable[Status],"<>Resolved",IntegrationRiskTable[Status],"<>Accepted",IntegrationRiskTable[Issue / decision],"<>",IntegrationRiskTable[Reviewer decision],"<>Remove")

## Integration Plan
Comprehensive Post-Deal Integration Checklist
Protect revenue while integrating cost. Each row is one action: give it an owner and a date before changing anything that already works. Yellow columns are yours to fill in.
ID | Phase | Workstream | Objective | Task | Ready evidence / deliverable | Dependency | Accountable owner | Target date | Status | Risk | Revenue impact | Workflow disposition | Synergy ID | DD issue ID | Decision / escalation | Notes | Reviewer decision
INT-001 | Diligence | Integration Thesis & Governance | Translate value into action | Write the integration thesis: what creates value, what must not break and what can wait. | Approved integration thesis | Deal thesis; diligence findings |  |  | Not Started | Critical | High | Preserve |  |  |  |  | Keep
INT-002 | Diligence | Integration Thesis & Governance | Define boundaries | Specify what integrates, remains standalone and requires further evidence. | Boundary decisions and rationale | Target operating model |  |  | Not Started | Critical | High | Preserve |  |  |  |  | Keep
INT-003 | Sign-to-Close | Integration Thesis & Governance | Establish accountability | Name executive sponsor, integration leader, IMO and workstream leads. | Signed governance charter | Leadership availability |  |  | Not Started | Critical | Medium | Standardize |  |  |  |  | Keep
INT-004 | Sign-to-Close | Integration Thesis & Governance | Set decision rights | Define which decisions sit with IMO, workstreams, business leaders and steering committee. | Decision-rights matrix | Governance charter |  |  | Not Started | High | Medium | Standardize |  |  |  |  | Keep
INT-005 | Sign-to-Close | Integration Thesis & Governance | Run operating cadence | Set weekly workstream reviews, dependency resolution and executive escalation. | Calendar; templates; first meeting complete | Lead appointments |  |  | Not Started | High | Low | Standardize |  |  |  |  | Keep
INT-006 | Day 1 | Integration Thesis & Governance | Establish control | Confirm legal control, signing authority, board changes and reserved matters. | Executed resolutions; authority matrix | Closing completed |  |  | Not Started | Critical | Medium | Standardize |  |  |  |  | Keep
INT-007 | Days 2-30 | Integration Thesis & Governance | Measure progress | Launch a dashboard for continuity, people, customers, risks, synergies and decisions. | Live dashboard with owners | Data availability |  |  | Not Started | High | Medium | Standardize |  |  |  |  | Keep
INT-008 | Post-100 | Integration Thesis & Governance | Close the program deliberately | Define exit criteria, transfer residual work to operators and capture lessons. | Closeout memo; BAU ownership | Workstream completion |  |  | Not Started | Medium | Low | Standardize |  |  |  |  | Keep
INT-009 | Diligence | Regulatory & Pre-Close Conduct | Plan within legal bounds | Have counsel define information sharing, clean teams and prohibited coordination. | Written protocol; trained team | Regulatory analysis |  |  | Not Started | Critical | High | Protect |  |  |  |  | Keep
INT-010 | Sign-to-Close | Regulatory & Pre-Close Conduct | Control sensitive data | Route pricing, customers, compensation and strategy through approved clean-team processes. | Access log; clean-team outputs | Counsel protocol |  |  | Not Started | Critical | High | Protect |  |  |  |  | Keep
INT-011 | Sign-to-Close | Regulatory & Pre-Close Conduct | Track approvals | Maintain filing, regulator request, remedy and approval milestones. | Regulatory tracker | Counsel and agency process |  |  | Not Started | Critical | High | Protect |  |  |  |  | Keep
INT-012 | Sign-to-Close | Regulatory & Pre-Close Conduct | Separate planning from operation | Prevent pre-close direction of the target's ordinary-course commercial decisions. | Decision log; training attestation | Counsel protocol |  |  | Not Started | Critical | High | Protect |  |  |  |  | Keep
INT-013 | Sign-to-Close | Day 1 Control & Continuity | Build critical-event list | Identify transactions that must work on Day 1: service, shipping, billing, cash, payroll and compliance. | Critical-event map | Workflow diligence |  |  | Not Started | Critical | High | Preserve |  |  |  |  | Keep
INT-014 | Sign-to-Close | Day 1 Control & Continuity | Run simulations | Dry-run critical transactions and failure escalation before close. | Simulation results; resolved gaps | System and owner access |  |  | Not Started | Critical | High | Protect |  |  |  |  | Keep
INT-015 | Day 1 | Day 1 Control & Continuity | Maintain customer delivery | Confirm orders, services, support and SLAs continue without interruption. | Operational signoff; live monitoring | People, systems, vendors |  |  | Not Started | Critical | High | Preserve |  |  |  |  | Keep
INT-016 | Day 1 | Day 1 Control & Continuity | Maintain cash operations | Confirm invoicing, collections, purchasing, payments and banking authorities work. | Treasury and finance signoff | Accounts and approvals |  |  | Not Started | Critical | High | Protect |  |  |  |  | Keep
INT-017 | Day 1 | Day 1 Control & Continuity | Open command center | Activate escalation channels, issue triage and executive coverage. | Command center roster; live issue log | Governance active |  |  | Not Started | High | High | Standardize |  |  |  |  | Keep
INT-018 | Days 2-30 | Day 1 Control & Continuity | Stabilize before changing | Resolve continuity defects before launching broad redesign. | Stable KPI trend; closed critical issues | Day 1 issue log |  |  | Not Started | Critical | High | Preserve |  |  |  |  | Keep
INT-019 | Sign-to-Close | Communications | Map stakeholders | Segment employees, customers, vendors, partners, lenders and regulators by need and timing. | Stakeholder map | Legal constraints |  |  | Not Started | High | High | Protect |  |  |  |  | Keep
INT-020 | Sign-to-Close | Communications | Prepare one narrative | Explain why the deal happened, what changes now, what does not and where questions go. | Approved message house and Q&A | Leadership alignment |  |  | Not Started | High | High | Preserve |  |  |  |  | Keep
INT-021 | Day 1 | Communications | Sequence announcements | Coordinate internal, customer, vendor, media and regulatory messages. | Delivery confirmations; response log | Closing announcement |  |  | Not Started | Critical | High | Protect |  |  |  |  | Keep
INT-022 | Days 2-30 | Communications | Listen and correct | Track recurring questions, rumors and resistance; update messages quickly. | Issue themes; updated Q&A | Feedback channels |  |  | Not Started | Medium | Medium | Protect |  |  |  |  | Keep
INT-023 | Diligence | Customers & Revenue | Identify revenue at risk | Rank customers by value, concentration, renewal, consent, relationship owner and change sensitivity. | Revenue-risk heat map | Customer diligence |  |  | Not Started | Critical | High | Protect |  |  |  |  | Keep
INT-024 | Sign-to-Close | Customers & Revenue | Assign coverage | Name executive and account owners for priority customer outreach. | Account coverage plan | Legal contact permissions |  |  | Not Started | Critical | High | Protect |  |  |  |  | Keep
INT-025 | Sign-to-Close | Customers & Revenue | Prepare consent plan | Secure required assignment or change-of-control consents with fallbacks. | Executed consents; fallback terms | Contract matrix |  |  | Not Started | Critical | High | Protect |  |  |  |  | Keep
INT-026 | Day 1 | Customers & Revenue | Reassure without overselling | Communicate continuity first; do not promise unready cross-sell or product changes. | Customer contact log | Approved messaging |  |  | Not Started | Critical | High | Preserve |  |  |  |  | Keep
INT-027 | Days 2-30 | Customers & Revenue | Monitor leading indicators | Track contacts, usage, tickets, pipeline, renewals, churn risk and collections daily or weekly. | Revenue continuity dashboard | Data feeds |  |  | Not Started | High | High | Protect |  |  |  |  | Keep
INT-028 | Days 31-60 | Customers & Revenue | Transfer relationships | Move account knowledge from individuals into teams, systems and documented plans. | Updated account plans; multi-threaded relationships | Retention and CRM access |  |  | Not Started | High | High | Protect |  |  |  |  | Keep
INT-029 | Days 61-100 | Customers & Revenue | Test selective growth | Pilot cross-sell or pricing actions with evidence and customer safeguards. | Pilot results; go/no-go decision | Stable base revenue |  |  | Not Started | High | High | Combine |  |  |  |  | Keep
INT-030 | Diligence | Sales, Marketing & Pricing | Protect the sales motion | Identify the practices and people actually producing bookings. | Sales workflow map | Commercial diligence |  |  | Not Started | Critical | High | Preserve |  |  |  |  | Keep
INT-031 | Sign-to-Close | Sales, Marketing & Pricing | Freeze risky changes | Avoid broad territory, compensation, brand or pricing changes before evidence. | Change-control rule | Integration thesis |  |  | Not Started | High | High | Preserve |  |  |  |  | Keep
INT-032 | Day 1 | Sales, Marketing & Pricing | Maintain access and tools | Confirm CRM, proposal, pricing, marketing and channel systems remain available. | Access signoff | IT readiness |  |  | Not Started | Critical | High | Protect |  |  |  |  | Keep
INT-033 | Days 2-30 | Sales, Marketing & Pricing | Reconcile pipeline | Normalize stage definitions, remove stale opportunities and preserve forecast accountability. | Reconciled pipeline and owners | CRM data |  |  | Not Started | High | High | Standardize |  |  |  |  | Keep
INT-034 | Days 31-60 | Sales, Marketing & Pricing | Design future coverage | Compare territories, roles, incentives and channels against the integration thesis. | Approved coverage design | Talent decisions; customer map |  |  | Not Started | High | High | Combine |  |  |  |  | Keep
INT-035 | Days 61-100 | Sales, Marketing & Pricing | Implement with guardrails | Roll out selected pricing, territory or compensation changes with churn and pipeline controls. | Implementation metrics | Approved design |  |  | Not Started | High | High | Standardize |  |  |  |  | Keep
INT-036 | Diligence | Product, Service & Brand | Identify value-bearing assets | Determine which products, services, brands, roadmaps and delivery practices drive the thesis. | Value-bearing asset map | Deal thesis |  |  | Not Started | Critical | High | Preserve |  |  |  |  | Keep
INT-037 | Sign-to-Close | Product, Service & Brand | Protect commitments | Inventory customer roadmap, SLA and delivery commitments. | Commitment register | Customer and product data |  |  | Not Started | High | High | Protect |  |  |  |  | Keep
INT-038 | Day 1 | Product, Service & Brand | Maintain delivery | Keep product release, service delivery, support and quality workflows operating. | Delivery signoff | People and systems |  |  | Not Started | Critical | High | Preserve |  |  |  |  | Keep
INT-039 | Days 2-30 | Product, Service & Brand | Resolve ownership | Name product, roadmap, brand and service decision owners. | Decision-rights map | Leadership design |  |  | Not Started | High | High | Standardize |  |  |  |  | Keep
INT-040 | Days 31-60 | Product, Service & Brand | Rationalize with evidence | Compare overlap, margin, customer reliance, technical debt and migration cost. | Portfolio decision memo | Customer evidence; economics |  |  | Not Started | High | High | Combine |  |  |  |  | Keep
INT-041 | Days 61-100 | Product, Service & Brand | Sequence migrations | Move customers or brands only when replacement quality and support capacity are proven. | Pilot and migration plan | Readiness evidence |  |  | Not Started | Critical | High | Retire |  |  |  |  | Keep
INT-042 | Diligence | Operations & Workflows | Map critical workflows | Capture trigger, inputs, owner, decisions, systems, exceptions, outputs and controls. | Workflow transferability map | Operational diligence |  |  | Not Started | Critical | High | Preserve |  |  |  |  | Keep
INT-043 | Sign-to-Close | Operations & Workflows | Assign disposition | Classify each workflow Preserve, Protect, Combine, Standardize or Retire. | Approved disposition register | Integration thesis |  |  | Not Started | Critical | High | Preserve |  |  |  |  | Keep
INT-044 | Day 1 | Operations & Workflows | Keep proven work running | Do not replace a revenue-producing workflow merely for uniformity. | Day 1 workflow signoff | Access and people continuity |  |  | Not Started | Critical | High | Preserve |  |  |  |  | Keep
INT-045 | Days 2-30 | Operations & Workflows | Observe before redesign | Measure actual throughput, defects, exceptions and manual effort. | Baseline KPI set; observation notes | Stable operations |  |  | Not Started | High | High | Protect |  |  |  |  | Keep
INT-046 | Days 31-60 | Operations & Workflows | Remove dependency | Document judgment, cross-train backups and reduce owner or vendor single points of failure. | Coverage evidence; revised SOP | Key-person retention |  |  | Not Started | Critical | High | Protect |  |  |  |  | Keep
INT-047 | Days 61-100 | Operations & Workflows | Standardize selectively | Change workflows only where evidence shows lower risk or better economics. | Approved future-state map; pilot result | Baseline and controls |  |  | Not Started | High | Medium | Standardize |  |  |  |  | Keep
INT-048 | Post-100 | Operations & Workflows | Codify reusable knowledge | Capture decision rules, edge cases, examples and quality evaluations for valuable workflows. | Versioned workflow asset | Rights and privacy clearance |  |  | Not Started | Medium | Medium | Protect |  |  |  |  | Keep
INT-049 | Diligence | People, Organization & Culture | Identify critical people | Tie talent to revenue, workflows, relationships, systems and institutional knowledge. | Critical-talent map | People diligence |  |  | Not Started | Critical | High | Protect |  |  |  |  | Keep
INT-050 | Sign-to-Close | People, Organization & Culture | Secure retention | Finalize retention, transition and knowledge-transfer plans for critical people. | Executed agreements; coverage plan | Budget and approvals |  |  | Not Started | Critical | High | Protect |  |  |  |  | Keep
INT-051 | Sign-to-Close | People, Organization & Culture | Design Day 1 organization | Name leaders and reporting lines needed for control without forcing premature redesign. | Day 1 org chart | Leadership decisions |  |  | Not Started | Critical | High | Preserve |  |  |  |  | Keep
INT-052 | Day 1 | People, Organization & Culture | Deliver employee experience | Confirm payroll, benefits, access, communications and manager support. | HR signoff; help channel live | HRIS and payroll readiness |  |  | Not Started | Critical | Medium | Protect |  |  |  |  | Keep
INT-053 | Days 2-30 | People, Organization & Culture | Clarify decision rights | Resolve duplicated or missing ownership and publish escalation paths. | Role and decision matrix | Day 1 observations |  |  | Not Started | High | Medium | Standardize |  |  |  |  | Keep
INT-054 | Days 31-60 | People, Organization & Culture | Build future organization | Use workload, capability and value—not titles alone—to design roles. | Future-state org and selection criteria | Operating model |  |  | Not Started | High | High | Combine |  |  |  |  | Keep
INT-055 | Days 61-100 | People, Organization & Culture | Manage exits carefully | Sequence reductions after knowledge, customer and control dependencies are covered. | Transition completion; risk signoff | Knowledge transfer |  |  | Not Started | Critical | High | Retire |  |  |  |  | Keep
INT-056 | Diligence | Technology & Systems | Define minimum viable integration | Identify systems that must connect at close and systems that should remain stable. | Technology Day 1 architecture | Application inventory |  |  | Not Started | Critical | High | Preserve |  |  |  |  | Keep
INT-057 | Sign-to-Close | Technology & Systems | Secure access | Prepare identities, privileged access, domains, repositories, backups and vendor support. | Access and credential runbook | Legal and cyber clearance |  |  | Not Started | Critical | High | Protect |  |  |  |  | Keep
INT-058 | Day 1 | Technology & Systems | Enable essential connectivity | Activate approved email, collaboration, reporting and support connections. | IT signoff | Network and identity readiness |  |  | Not Started | Critical | Medium | Combine |  |  |  |  | Keep
INT-059 | Days 2-30 | Technology & Systems | Stabilize incidents | Track failures, capacity, security and support demand before migrations. | Incident trend; stability signoff | Live operations |  |  | Not Started | High | High | Protect |  |  |  |  | Keep
INT-060 | Days 31-60 | Technology & Systems | Choose system of record | Decide application-by-application using capability, risk, cost, data and migration evidence. | System disposition register | Business workflow decisions |  |  | Not Started | High | High | Standardize |  |  |  |  | Keep
INT-061 | Days 61-100 | Technology & Systems | Pilot migrations | Test data, controls, performance and user readiness before cutover. | Pilot results; rollback plan | Approved target architecture |  |  | Not Started | Critical | High | Combine |  |  |  |  | Keep
INT-062 | Post-100 | Technology & Systems | Retire safely | Decommission only after records, interfaces, access and retention obligations are resolved. | Decommission certificate | Successful migration |  |  | Not Started | High | Medium | Retire |  |  |  |  | Keep
INT-063 | Diligence | Cyber, Privacy & Data | Carry findings forward | Convert each cyber, privacy and data issue into a Day 1 or remediation action. | Issue-to-action map | Diligence issue log |  |  | Not Started | Critical | High | Protect |  |  |  |  | Keep
INT-064 | Sign-to-Close | Cyber, Privacy & Data | Prepare incident coordination | Align contacts, notification rules, insurers, counsel and forensic support. | Incident runbook | Legal and IT teams |  |  | Not Started | Critical | High | Protect |  |  |  |  | Keep
INT-065 | Day 1 | Cyber, Privacy & Data | Establish secure control | Confirm privileged access, monitoring, backups and critical vendor coverage. | Security signoff | Credential transfer |  |  | Not Started | Critical | High | Protect |  |  |  |  | Keep
INT-066 | Days 2-30 | Cyber, Privacy & Data | Close critical gaps | Prioritize exploitable vulnerabilities, unsupported systems and missing access controls. | Remediation evidence | Risk-ranked findings |  |  | Not Started | Critical | High | Protect |  |  |  |  | Keep
INT-067 | Days 31-60 | Cyber, Privacy & Data | Integrate data governance | Align inventories, retention, permissions, consent and cross-border controls. | Approved data-governance map | Legal basis and contracts |  |  | Not Started | High | High | Standardize |  |  |  |  | Keep
INT-068 | Days 61-100 | Cyber, Privacy & Data | Govern AI use | Inventory models and vendors; define approved data, human review and evaluation requirements. | AI governance register | Data-rights review |  |  | Not Started | High | Medium | Protect |  |  |  |  | Keep
INT-069 | Diligence | Finance, Controls & Reporting | Preserve visibility | Design a standalone operating and financial view for up to six months where useful. | Reporting design and exit criteria | Diligence financial model |  |  | Not Started | Critical | High | Preserve |  |  |  |  | Keep
INT-070 | Sign-to-Close | Finance, Controls & Reporting | Prepare opening control | Plan chart-of-accounts mapping, consolidation, cutoff and opening balance sheet. | Close and reporting calendar | Accounting-policy decisions |  |  | Not Started | Critical | Medium | Standardize |  |  |  |  | Keep
INT-071 | Day 1 | Finance, Controls & Reporting | Activate authority | Update banking, payments, purchasing limits, signatories and approval matrices. | Authority signoff | Legal close and bank access |  |  | Not Started | Critical | High | Standardize |  |  |  |  | Keep
INT-072 | Days 2-30 | Finance, Controls & Reporting | Complete first close | Run a controlled month-end close with reconciliations and issue review. | Closed books; reconciliation signoff | System and people readiness |  |  | Not Started | Critical | Medium | Protect |  |  |  |  | Keep
INT-073 | Days 31-60 | Finance, Controls & Reporting | Normalize performance view | Reconcile management reporting, KPIs, standalone results and synergy baselines. | Approved performance pack | First close |  |  | Not Started | High | High | Standardize |  |  |  |  | Keep
INT-074 | Days 61-100 | Finance, Controls & Reporting | Integrate controls deliberately | Align policies and controls after understanding target workflows and materiality. | Control migration evidence | Stable reporting |  |  | Not Started | High | Medium | Standardize |  |  |  |  | Keep
INT-075 | Sign-to-Close | Tax, Treasury & Banking | Plan entity and tax steps | Sequence elections, registrations, intercompany, payroll and indirect tax changes. | Tax integration plan | Legal structure |  |  | Not Started | High | Low | Standardize |  |  |  |  | Keep
INT-076 | Day 1 | Tax, Treasury & Banking | Control cash | Confirm cash visibility, bank access, funding, FX and payment controls. | Daily cash report; authority signoff | Bank readiness |  |  | Not Started | Critical | High | Protect |  |  |  |  | Keep
INT-077 | Days 2-30 | Tax, Treasury & Banking | Meet obligations | Complete required filings, notifications and payment-calendar transitions. | Filing confirmations | Tax data and advisors |  |  | Not Started | High | Medium | Protect |  |  |  |  | Keep
INT-078 | Days 31-60 | Tax, Treasury & Banking | Optimize structure carefully | Evaluate cash pooling, entity rationalization and tax opportunities after continuity. | Approved optimization memo | Stable operations |  |  | Not Started | Medium | Low | Combine |  |  |  |  | Keep
INT-079 | Sign-to-Close | Legal, Contracts & Compliance | Track consents and obligations | Complete assignments, notices, permits, licenses and closing conditions. | Executed consent and permit tracker | Counterparties and regulators |  |  | Not Started | Critical | High | Protect |  |  |  |  | Keep
INT-080 | Day 1 | Legal, Contracts & Compliance | Maintain compliance ownership | Name responsible officers and keep reporting, licensing and policy controls active. | Compliance signoff | People and authority |  |  | Not Started | Critical | High | Protect |  |  |  |  | Keep
INT-081 | Days 2-30 | Legal, Contracts & Compliance | Reconcile obligations | Centralize key terms, renewals, disputes and post-close covenants. | Obligation calendar | Contract repository access |  |  | Not Started | High | High | Standardize |  |  |  |  | Keep
INT-082 | Days 31-60 | Legal, Contracts & Compliance | Align policies | Harmonize only after confirming local law, customer terms and operating reality. | Approved policy map | Legal review |  |  | Not Started | High | Medium | Standardize |  |  |  |  | Keep
INT-083 | Days 61-100 | Legal, Contracts & Compliance | Simplify entities selectively | Rationalize entities and agreements without interrupting licenses, tax or contracts. | Executed rationalization plan | Regulatory and tax clearance |  |  | Not Started | High | Medium | Retire |  |  |  |  | Keep
INT-084 | Sign-to-Close | Vendors, Supply Chain & Facilities | Protect supply continuity | Confirm critical suppliers, orders, consents, inventory and logistics for close. | Supplier continuity signoff | Vendor diligence |  |  | Not Started | Critical | High | Protect |  |  |  |  | Keep
INT-085 | Day 1 | Vendors, Supply Chain & Facilities | Keep ordinary transactions moving | Ensure purchasing, receiving, payment, shipping and site access work. | Operational signoff | Systems and authority |  |  | Not Started | Critical | High | Preserve |  |  |  |  | Keep
INT-086 | Days 2-30 | Vendors, Supply Chain & Facilities | Validate baselines | Reconcile spend, terms, service levels, capacity and failure points. | Validated vendor/spend baseline | AP and contract data |  |  | Not Started | High | High | Protect |  |  |  |  | Keep
INT-087 | Days 31-60 | Vendors, Supply Chain & Facilities | Pursue low-risk leverage | Consolidate spend where continuity, quality and customer impact are protected. | Sourcing wave plan | Baseline and alternatives |  |  | Not Started | High | Medium | Combine |  |  |  |  | Keep
INT-088 | Days 61-100 | Vendors, Supply Chain & Facilities | Sequence footprint changes | Change facilities or suppliers only after dependencies and transition costs are proven. | Approved transition plan | Workflow and people mapping |  |  | Not Started | Critical | High | Retire |  |  |  |  | Keep
INT-089 | Diligence | Synergies & Value Capture | Validate each synergy | Require baseline, action, owner, timing, one-time cost, dependency and revenue-risk test. | Underwritten synergy register | Diligence data |  |  | Not Started | Critical | High | Protect |  |  |  |  | Keep
INT-090 | Sign-to-Close | Synergies & Value Capture | Lock baselines | Agree source data, calculation method and signoff before results move. | Baseline signoff | Finance and workstream owners |  |  | Not Started | Critical | Medium | Standardize |  |  |  |  | Keep
INT-091 | Days 2-30 | Synergies & Value Capture | Launch tracking | Track actions and realized results separately; do not count announcements as savings. | Live synergy tracker | Governance and finance |  |  | Not Started | High | Medium | Standardize |  |  |  |  | Keep
INT-092 | Days 31-60 | Synergies & Value Capture | Resolve leakage | Identify delay, dis-synergy, one-time cost and revenue impact against plan. | Variance and action log | Monthly actuals |  |  | Not Started | High | High | Protect |  |  |  |  | Keep
INT-093 | Days 61-100 | Synergies & Value Capture | Reforecast honestly | Update timing and value from evidence without preserving an obsolete deal case. | Approved reforecast | Realized data |  |  | Not Started | High | Medium | Standardize |  |  |  |  | Keep
INT-094 | Post-100 | Synergies & Value Capture | Embed ownership | Move recurring value-capture measures into normal business reviews. | BAU KPI ownership | Stable processes |  |  | Not Started | Medium | Medium | Standardize |  |  |  |  | Keep
INT-095 | Sign-to-Close | TSA & Separation | Define services precisely | For carve-outs, specify service, SLA, volume, price, term, owner, data and exit requirement. | Executed TSA schedule | Seller capability |  |  | Not Started | Critical | High | Protect |  |  |  |  | Keep
INT-096 | Day 1 | TSA & Separation | Activate governance | Confirm service contacts, incident escalation, billing and change control. | TSA governance live | Closing complete |  |  | Not Started | Critical | High | Protect |  |  |  |  | Keep
INT-097 | Days 2-30 | TSA & Separation | Validate consumption | Confirm actual service volume, quality, dependencies and hidden manual support. | TSA performance baseline | Service data |  |  | Not Started | High | High | Protect |  |  |  |  | Keep
INT-098 | Days 31-60 | TSA & Separation | Build exit path | Name replacement solution, milestones, data migration, testing and acceptance. | TSA exit plan | Target systems and resources |  |  | Not Started | Critical | High | Combine |  |  |  |  | Keep
INT-099 | Days 61-100 | TSA & Separation | Exit without cliff risk | Terminate only after parallel run, acceptance and rollback readiness. | Exit certificate | Successful testing |  |  | Not Started | Critical | High | Retire |  |  |  |  | Keep
INT-100 | Days 2-30 | Performance & Review | Compare evidence to thesis | Re-underwrite early operating results, customer signals and key-person stability. | 30-day thesis update | Dashboard and issue log |  |  | Not Started | High | High | Preserve |  |  |  |  | Keep
INT-101 | Days 31-60 | Performance & Review | Decide from observed reality | Approve, delay or stop major integration moves based on measured outcomes. | 60-day decision memo | Baseline and pilots |  |  | Not Started | High | High | Protect |  |  |  |  | Keep
INT-102 | Days 61-100 | Performance & Review | Confirm operating model | Lock the future-state design only after continuity and evidence support it. | 100-day operating model | Workstream evidence |  |  | Not Started | Critical | High | Standardize |  |  |  |  | Keep
INT-103 | Post-100 | Performance & Review | Audit value creation | Compare purchase thesis, realized standalone performance, synergies and dis-synergies. | Post-close value review | Finance and operating data |  |  | Not Started | High | High | Standardize |  |  |  |  | Keep
INT-104 | Post-100 | Performance & Review | Capture institutional memory | Record what was believed, learned, changed and should become reusable deal workflow. | Lessons-learned package | Workstream closeout |  |  | Not Started | Medium | Low | Protect |  |  |  |  | Keep

## Day 1 Readiness
Day 1 Readiness Gates
Day 1 means control and continuity. Integration continues after the business is safely operating.
Checkpoint | Timing | Question | Ready evidence | Owner | Status | Red flag / gap | Escalation | Reviewer decision
Legal control | Day 1 | Are legal control, boards, officers, authority and reserved matters effective? | Executed closing and authority documents |  | Not Started |  |  | Keep
People | Day 1 | Can every employee work, get paid, access benefits and reach a manager? | HR, payroll and access signoff |  | Not Started |  |  | Keep
Customers | Day 1 | Can customers buy, receive service, get support, be billed and make payments? | Customer journey simulation |  | Not Started |  |  | Keep
Revenue | Day 1 | Are priority accounts covered and required consents completed? | Account coverage and consent tracker |  | Not Started |  |  | Keep
Cash | Day 1 | Can the business invoice, collect, purchase, pay and fund operations? | Treasury and finance simulation |  | Not Started |  |  | Keep
Technology | Day 1 | Are identity, email, critical systems, admin access and support ready? | IT access and continuity signoff |  | Not Started |  |  | Keep
Cyber | Day 1 | Are monitoring, incident response, backups and privileged access controlled? | Security signoff |  | Not Started |  |  | Keep
Operations | Day 1 | Can critical workflows run and escalate exceptions without the seller? | Live workflow simulations |  | Not Started |  |  | Keep
Vendors | Day 1 | Will critical suppliers, logistics, facilities and outsourced services continue? | Vendor and site continuity signoff |  | Not Started |  |  | Keep
Compliance | Day 1 | Are licenses, permits, reporting and responsible officers in place? | Legal and compliance signoff |  | Not Started |  |  | Keep
Communications | Day 1 | Are stakeholder messages sequenced, approved and owned? | Message house, Q&A and delivery plan |  | Not Started |  |  | Keep
Governance | Day 1 | Are the command center, issue log, escalation and executive coverage active? | IMO readiness signoff |  | Not Started |  |  | Keep

## Workflow Decisions
Workflow Integration Decisions
Protect revenue while integrating cost: decide workflow by workflow, then change only with evidence.
Workflow ID | Workflow | Current owner | Business objective | Revenue / customer impact | Day 1 rule | Disposition | Disposition rationale | Future owner | Systems | People / knowledge dependency | Rights / privacy constraint | Control / KPI | Transition milestone | Rollback / contingency | Status | Reviewer decision
WF-01 | Lead to opportunity |  |  |  | Preserve until evidence supports change | Preserve | [8 empty] | Not Started | Keep
WF-02 | Opportunity to contract |  |  |  | Preserve until evidence supports change | Preserve | [8 empty] | Not Started | Keep
WF-03 | Contract to cash |  |  |  | Preserve until evidence supports change | Preserve | [8 empty] | Not Started | Keep
WF-04 | Customer onboarding |  |  |  | Preserve until evidence supports change | Preserve | [8 empty] | Not Started | Keep
WF-05 | Customer support and escalation |  |  |  | Preserve until evidence supports change | Preserve | [8 empty] | Not Started | Keep
WF-06 | Product / content creation |  |  |  | Preserve until evidence supports change | Preserve | [8 empty] | Not Started | Keep
WF-07 | Release or service delivery |  |  |  | Preserve until evidence supports change | Preserve | [8 empty] | Not Started | Keep
WF-08 | Procure to pay |  |  |  | Preserve until evidence supports change | Preserve | [8 empty] | Not Started | Keep
WF-09 | Vendor onboarding |  |  |  | Preserve until evidence supports change | Preserve | [8 empty] | Not Started | Keep
WF-10 | Hire to payroll |  |  |  | Preserve until evidence supports change | Preserve | [8 empty] | Not Started | Keep
WF-11 | Month-end close and reporting |  |  |  | Preserve until evidence supports change | Preserve | [8 empty] | Not Started | Keep
WF-12 | Data intake to approved use |  |  |  | Preserve until evidence supports change | Preserve | [8 empty] | Not Started | Keep
WF-13 | Security incident response |  |  |  | Preserve until evidence supports change | Preserve | [8 empty] | Not Started | Keep
WF-14 | Regulatory reporting |  |  |  | Preserve until evidence supports change | Preserve | [8 empty] | Not Started | Keep

## Synergies
Synergy & Value-Capture Register
Enter only underwritten synergies. Baseline and Target are annual amounts in the same units (for a cost line: today's cost and the cost after the change; for revenue: today's revenue and the target). Annual benefit and Realized % calculate themselves. Enter a dis-synergy as lost revenue.
Synergy ID | Type | Thesis | Baseline source | Baseline (annual) | Target (annual) | One-time cost | Start date | Run-rate date | Accountable owner | Key action | Dependency | Revenue / customer risk | Realized to date (annual run-rate) | Status | Reviewer decision | Annual benefit | Realized %
SYN-001 | Cost | [12 empty] | Not Started | Keep
SYN-002 | Cost | [12 empty] | Not Started | Keep
SYN-003 | Cost | [12 empty] | Not Started | Keep
SYN-004 | Cost | [12 empty] | Not Started | Keep
SYN-005 | Cost | [12 empty] | Not Started | Keep
SYN-006 | Cost | [12 empty] | Not Started | Keep
SYN-007 | Cost | [12 empty] | Not Started | Keep
SYN-008 | Cost | [12 empty] | Not Started | Keep
SYN-009 | Cost | [12 empty] | Not Started | Keep
SYN-010 | Cost | [12 empty] | Not Started | Keep
SYN-011 | Cost | [12 empty] | Not Started | Keep
SYN-012 | Cost | [12 empty] | Not Started | Keep
SYN-013 | Cost | [12 empty] | Not Started | Keep
SYN-014 | Cost | [12 empty] | Not Started | Keep
SYN-015 | Cost | [12 empty] | Not Started | Keep
SYN-016 | Cost | [12 empty] | Not Started | Keep
SYN-017 | Cost | [12 empty] | Not Started | Keep
SYN-018 | Cost | [12 empty] | Not Started | Keep
SYN-019 | Cost | [12 empty] | Not Started | Keep
SYN-020 | Cost | [12 empty] | Not Started | Keep
SYN-021 | Cost | [12 empty] | Not Started | Keep
SYN-022 | Cost | [12 empty] | Not Started | Keep
SYN-023 | Cost | [12 empty] | Not Started | Keep
SYN-024 | Cost | [12 empty] | Not Started | Keep
SYN-025 | Cost | [12 empty] | Not Started | Keep
SYN-026 | Cost | [12 empty] | Not Started | Keep
SYN-027 | Cost | [12 empty] | Not Started | Keep
SYN-028 | Cost | [12 empty] | Not Started | Keep
SYN-029 | Cost | [12 empty] | Not Started | Keep
SYN-030 | Cost | [12 empty] | Not Started | Keep
SYN-031 | Cost | [12 empty] | Not Started | Keep
SYN-032 | Cost | [12 empty] | Not Started | Keep
SYN-033 | Cost | [12 empty] | Not Started | Keep
SYN-034 | Cost | [12 empty] | Not Started | Keep
SYN-035 | Cost | [12 empty] | Not Started | Keep
SYN-036 | Cost | [12 empty] | Not Started | Keep
SYN-037 | Cost | [12 empty] | Not Started | Keep
SYN-038 | Cost | [12 empty] | Not Started | Keep
SYN-039 | Cost | [12 empty] | Not Started | Keep
SYN-040 | Cost | [12 empty] | Not Started | Keep

## Risks & Decisions
Integration Risk & Decision Log
Use this tab only for material findings. Every item needs evidence, an owner and a decision.
Issue ID | Integration ID | Workstream | Issue / decision | Evidence | Severity | Revenue impact | Decision required | Escalation owner | Due date | Resolution | Status | Reviewer decision
RID-001 | [10 empty] | Open | Keep
RID-002 | [10 empty] | Open | Keep
RID-003 | [10 empty] | Open | Keep
RID-004 | [10 empty] | Open | Keep
RID-005 | [10 empty] | Open | Keep
RID-006 | [10 empty] | Open | Keep
RID-007 | [10 empty] | Open | Keep
RID-008 | [10 empty] | Open | Keep
RID-009 | [10 empty] | Open | Keep
RID-010 | [10 empty] | Open | Keep
RID-011 | [10 empty] | Open | Keep
RID-012 | [10 empty] | Open | Keep
RID-013 | [10 empty] | Open | Keep
RID-014 | [10 empty] | Open | Keep
RID-015 | [10 empty] | Open | Keep
RID-016 | [10 empty] | Open | Keep
RID-017 | [10 empty] | Open | Keep
RID-018 | [10 empty] | Open | Keep
RID-019 | [10 empty] | Open | Keep
RID-020 | [10 empty] | Open | Keep
RID-021 | [10 empty] | Open | Keep
RID-022 | [10 empty] | Open | Keep
RID-023 | [10 empty] | Open | Keep
RID-024 | [10 empty] | Open | Keep
RID-025 | [10 empty] | Open | Keep
RID-026 | [10 empty] | Open | Keep
RID-027 | [10 empty] | Open | Keep
RID-028 | [10 empty] | Open | Keep
RID-029 | [10 empty] | Open | Keep
RID-030 | [10 empty] | Open | Keep
RID-031 | [10 empty] | Open | Keep
RID-032 | [10 empty] | Open | Keep
RID-033 | [10 empty] | Open | Keep
RID-034 | [10 empty] | Open | Keep
RID-035 | [10 empty] | Open | Keep
RID-036 | [10 empty] | Open | Keep
RID-037 | [10 empty] | Open | Keep
RID-038 | [10 empty] | Open | Keep
RID-039 | [10 empty] | Open | Keep
RID-040 | [10 empty] | Open | Keep